## Slide 1
A
Duration 5
B
Duration 8
C
Duration 4
D
Duration 3
E
Duration 8
ES 0
ES 5
ES 5
ES 13
ES 16
LF 24
LF 16
LF 13
LF 13
LF 5
TF = 0
FF = 0
TF = 0
FF = 0
TF = 4
FF = 4
TF = 0
FF = 0
TF = 0
Forwards Pass – Start first activity on day 0 (Early Start = ES)
Early Finish (EF) = Early Start + Duration
Backwards Pass – Last activity EF = Late Finish (LF)
Late Start (LS) = LF – Duration
Successor activity ES date = EF of predecessor (if multiple predecessors, use the higher number)
Total Float (TF) calculated by LF – EF (Definition: how long can the activity be delayed without affecting the project completion date
Free Float (FF) calculated by taking EF and subtracting it from its successor activities ES (Definition: how long can I delay this activity without affecting the early start date of an immediate successor activity
Critical Path – longest chain of activities with the least amount of float. Most often, critical path has ZERO float. Any delays to activities on critical path usually correlates to a change to the go live date unless other action is taken to get the schedule back on track
EF 5
EF 13
EF 9
EF 16
EF 24
LS 16
LS 13
LS 9
LS 5
LS 0