## Slide 1
1 Win
1 Win
5 Win Total
1 Win
1 Win
1 Win
10
10
50
10
10
10
Mon
Tue
Wed
Thu
Fri
Schedule Baseline
Cost Baseline (budgeted rate)
End of Wed
Completed 2 windows
PV – how much $ should I have completed according to baselines =
EV – how much $ was actually completed at budgeted rate =
AC – how much did I actually pay for completed work =
BAC – Budget at Completion =
EAC – Total cost forecast =
$50
$30
15
15
$20
$30
$60 or $75 (4 Formulas)
ETC –how much will I spend for the remaining work =
$30 or $45
SV – how far am I ahead or behind schedule? (SV = EV - PV)
SPI – how efficient have I been from a schedule perspective? (SPI = EV / PV)
CV – how far am I over or under budget? (CV = EV - AC)
CPI – how efficient have I been from a cost perspective? (CPI = EV / AC)
= -$10
= 0.66
= -$10
= 0.66
EAC Formulas:
1. Typical variances: EAC = BAC/CPI
2. Atypical variances: EAC = AC+ (BAC - EV)
3. Typical variances for cost and schedule: EAC = AC + ((BAC – EV)/ (CPI * SPI))
4. Most accurate but not used to calculate on exam:
EAC = AC + Bottom-up ETC (rollup WBS)
ETC Formula:
ETC = EAC – AC
Variances:
Schedule Variance: SV = EV – PV
Cost Variance: CV = EV – AC
Indexes:
Schedule Performance Index: SPI = EV / PV
Cost Performance Index: CPI = EV / AC
Definitions:
Planned Value (PV): How much $ should have been earned according to the plan
Earned Value (EV): How much $ has been completed at the budgeted rate (actual units x budgeted unit rate)
Actual Cost (AC): How much money did the work performed actually cost
Budget at Completion (BAC): Cost Baseline