## Slide 1
5
15
7
10
3
30% risk
of 3 day
delay
70% risk
of 5 day
delay
20% risk
of 1 day
delay
40% risk
of 2 day
delay
50% risk
of 5 day
delay
Schedule Baseline
40 Days
Iteration
1
Random 65%
No delay
5 DAY ACTIVITY
Random 42%
5 day delay
20 DAY ACTIVITY
Random 94%
No delay
7 DAY ACTIVITY
Random 71%
No delay
10 DAY ACTIVITY
Random 25%
5 day delay
8 DAY ACTIVITY
Monte Carlo Run 1
50 Days
Iteration
2
Random 15%
No delay
8 DAY ACTIVITY
Random 55%
5 day delay
20 DAY ACTIVITY
Random 6%
1 day delay
8 DAY ACTIVITY
Random 85%
No delay
10 DAY ACTIVITY
Random 52%
No delay
3 DAY ACTIVITY
Monte Carlo Run 2
49 Days
Iteration
3
Random 92%
No delay
8 DAY ACTIVITY
Random 25%
5 day delay
20 DAY ACTIVITY
Random 17%
1 day delay
8 DAY ACTIVITY
Random 35%
2 day delay
12 DAY ACTIVITY
Random 48%
5 day delay
8 DAY ACTIVITY
Monte Carlo Run 3
56 Days
Iteration
4
Random 42%
No delay
8 DAY ACTIVITY
Random 80%
No delay
15 DAY ACTIVITY
Random 29%
No delay
7 DAY ACTIVITY
Random 45%
No delay
10 DAY ACTIVITY
Random 63%
No delay
3 DAY ACTIVITY
Monte Carlo Run 3
40 Days
Monte Carlo Average 48.75 Days: 21.9% Project Go Live Delay Predicted
Monte Carlo Simulation: Simplified for Understanding