## Slide 1
a
10
12
8
6
4
Resource Optimization Techniques
M
T
W
T
F
Activity A
5 Days – Critical Path Activity
Holiday Party
@ 12PM

## Slide 2
a
10
12
8
6
4
Resource Leveling
M
T
W
T
F
Activity A
5 Days – Critical Path Activity
Holiday Party
@ 12PM

## Slide 3
a
8
8
8
8
4
Resource Leveling
M
T
W
T
F
4
M
Holiday Party
@ 12PM
Activity A
6 Days – Critical Path Activity

## Slide 4
a
10
12
8
6
4
Resource Smoothing
M
T
W
T
F
Activity A
5 Days – Critical Path Activity
Holiday Party
@ 12PM

## Slide 5
a
10
12
8
6
4
Resource Smoothing
M
T
W
T
F
Activity A
5 Days – Critical Path Activity
Holiday Party
@ 12PM

## Slide 6
a
8
8
8
8
8
Resource Smoothing
M
T
W
T
F
No
Holiday Party
@ 12PM
Activity A
5 Days – Critical Path Activity

## Slide 7
Paint Ceiling
4 Days
2 People
Paint Walls
4 Days
2 People
Replace Carpet
4 Days
2 People
Paint Ceiling
3 Days
4 People
Paint Walls
3 Days
4 People
Replace Carpet
3 Days
4 People
Paint Ceiling
4 Days
2 People
Paint Walls
4 Days
2 People
Replace Carpet
4 Days
2 People
Scenario 1
Normal Schedule
12 Days
Scenario 2
Crashing
9 Days
Scenario 2
Fast-tracking
8 Days
24
Days $
24
Days $
36
Days $
Schedule Compression Techniques