## RR
IDENTIFY RISK |  |  |  | QUALITATIVE RISK ANALYSIS | [7 empty] | QUANTITATIVE |  | PLAN RISK RESPONSES |  | QUALITATIVE | Plan Risk Responses
# | O / T | Risk Name | Detailed Description | RBS | WBS | Prob | Impact | Risk Score | Prob (%) | Impact $ | Impact (Wks) | Cont $ | Cont Wks | Risk Strategy | Response | Risk Owner | Risk Trigger | Status | Date Last Updated | Comments
2 | T | Implementation PartnerAcquired | As a result of our implementation partner being acquired, less attention may be given to our organization's implementation, which would lead cost overruns and schedule delays. | 1.4 | 1.5.1 | 4 | 4 | 16 | 50% | -300000 | -12 | -150000 | -6 | Mitigate | Utilize new implementation partner | PM | Behind schedule more than 15% | Open | 2020-06-01
1 | T | Outdated Microsoft Exchange | As a result of having an outdated version of Microsoft Exchange, failure to automatically email customers may occur, which would lead to frustrated customers and missed sales opportunities. | 1.2 | 1.2.2 | 3 | 2 | 6 | 50% | -50000 | -4 | -25000 | -2 | Avoid | Implement new version of Exchange | IT Manager | None - Implementing Exchange | Open | 2020-06-25
3 | T | Lightning Interface | As a result of the Lightning Interface's release delay, full integration with our phone system may not be possible, which will lead to incomplete scope, cost overruns, and schedule delays. | 1.3 | 1.3.1 | 1 | 2 | 2 | 10% | -75000 | -4 | -7500 | -0.4 | Mitigate | Modify phone and Salesforce code | Dir of App Dev | Announcement by Salesforce that Lightning will be delayed till Q2 | Open | 2020-05-25
[12 empty] | -182500 | -8.4
Definitions of Probability and Impact
[9 empty] | Score | Prob % | Impact $ | Impact Wks
[9 empty] | 5 | > 70 | > 400K | > 12
[9 empty] | 4 | 45-70 | 200K-400K | 10-12
[9 empty] | 3 | 31-45 | 100k-199K | 6-9
[9 empty] | 2 | 20-30 | 50k-99K | 2-5
[9 empty] | 1 | < 20 | < 50K | < 2
Probability and Impact Matrix
|  |  |  | Prob | Score
|  |  |  | 5 | 5 | 10 | 15 | 20 | 25
|  |  |  | 4 | 4 | 8 | 12 | 16 | 20
|  |  |  | 3 | 3 | 6 | 9 | 12 | 15
|  |  |  | 2 | 2 | 4 | 6 | 8 | 10
|  |  |  | 1 | 1 | 2 | 3 | 4 | 5
|  |  |  | Impact | 1 | 2 | 3 | 4 | 5